## Sheet1
Risk | Type of Risk | Recognition Date | Probability of Occurence | Priority | Severity | Owner | Action & Response | Risk Loss Size (days) | Project Impact of Response | Prevention | Residual Risk | Status
Snow Day | Project | 2018-01-30 | 20% | 2 | 3 | Brad | Meeting via Slack | 0 | Low/None | N/A | None | Unacknowledged
Issues with Database (multiple) | Technical | 2018-01-30 | 20% | 1 | 2 | Anthony | Attempt restore from snapshot | 1 | High | Make sure data is validated | Medium | Unacknowledged
Requirement change | Business | 2018-01-30 | 75-80% | 2 | 2 | Matt | Meet with Client and Team | 2018-01-02 | High | N/A | Medium | Unacknowledged
Loss of connection to University hosting | Technical | 2018-01-30 | 30% | 3 | 3 | Jordan | Meet via Slack off campus | 0 | Low/None | Communicate in class | None | Unacknowledged
Loss of access to GitHub | Technical | 2018-01-30 | >1.00% | 2 | 1 | Brad | Email GitHub Service | 1 | High | N/A | Medium | Unacknowledged
Unavailable Client | Business | 2018-01-30 | 10% | 2 | 1 | Sam | Reschedule Meeting | 2018-01-02 | High | N/A | Low | Occured on 2/1
Tools cause compatability issues | Technical | 2018-01-30 | 15% | 3 | 1 | Jordan | Attempt to resolve issues with tool | 2018-01-02 | High | Maintain compatable tools | Low | Unacknowledged
Sick Day | Project | 2018-01-30 | 10% | 3 | 3 | Brad | Reschedule tasks or meeting | 2018-01-02 | Medium | washing hands daily | Low | Unacknowledged
Backups Unavailable | Technical | 2018-01-30 | 5% | 3 | 2 | Anthony | Restore from snapshot, make new backup schedule | 2018-01-02 | Medium | Make sure backups run | Medium | Unacknowledged
Unable to fulfill requirement | Technical | 2018-01-30 | 5% | 3 | 3 | Matt | Ask client for clarification/modification | 2018-01-02 | High | N/A | Medium | Unacknowledged
Team unavailability | Business | 2018-01-30 | 10% | 4 | 2 | Matt | Hold teambuilding exercise | 2 | Medium | Resolve issues quickly | Low | Unacknowledged
Timeline Delayed/Changed | Project | 2018-01-30 | 50.5% | 1 | 3 | Sam | Immediate Response from Team | 0 | High | Constant Communication | Low | Unacknowledged
Meeting Times Unavailable | Business | 2018-01-30 | 20% | 2 | 2 | Brad | Make a new meeting time, When2Meet | 1 | Medium | When2Meet for Meetings | Low | Unacknowledged
Budget too low | Project | 2018-01-30 | 20% | 2 | 3 | Matt | Request more funds | 5 | High | Try to plan for future costs | Low | Unacknowledged
Hardware unavailable | Technical | 2018-01-30 | 5% | 2 | 2 | Anthony | Find alternative hardware | 5 | High | N/A | Medium | Unacknowledged